## Sheet1
Project 2 Team 1
Backlog
Group | ID | Story | Est. Time | Priority
Game Mechanics | 1
| 1.1 | I want to be able to represent a five in a row game board and all of its pieces in a game state object | 4 | 1.1
| 1.2 | I want to be able to print the game state to the console, with white pieces showing 0, black pieces showing @ and blank pieces showing + | 1 | 1.2
| 1.3 | I want to be able to make moves by placing pieces on the board | 1 | 1.3
| 1.4 | I want to be able to check the legality of placing pieces on the board, and prevent illegal moves | 3 | 1.4
| 1.5 | I want to see(reprint) the board anytime a new move is made | 1 | 1.5
| 1.6 | I want to know when a win, lose, or tie game state has been reached | 3 | 1.6
| 1.7 | I want to be able to undo up to 10 moves by me | 2 | 1.7
| 1.8 | I want to be able to request a list of possible moves so that it is easier to determine the best move | 2 | 1.8
| 1.9 | I want to be able to see a report of the game after completion, with things such as win lose or tie and number of moves made or time until game completion. | 3 | 1.9
| 1.1 | I want to be able to save and open gamestates (optional) | 2 | 1.1
Game Server | 2
| 2.1 | I want to be able to create connections(open ip sockets) with clients | 2 | 2.1
| 2.2 | I want to be able to read messages from client | 1 | 2.2
| 2.3 | I want to be able to write messages to client | 1 | 2.3
| 2.4 | I want to be able to parse client read messages for meaningful information such as commands or moves | 3 | 2.4
| 2.5 | I want to be able to report a failed parse to the client | 1 | 2.5
| 2.6 | I want to be able to implement clients commands and moves in our game engine | 3 | 2.6
| 2.7 | I want to respond(write to client) with a meaningful message upon implementation of commands or moves | 1 | 2.7
| 2.8 | I want to be able to support multiple clients (optional) | 4 | 2.8
Game AI | 3
| 3.1 | I want to play against an EASY AI, one who makes random moves in proximity to player pieces, but will still block obvious player wins in one move | 3 | 3.1
| 3.2 | I want to have a simple evaluation function that can tell me how good the board state is for me, without look ahead | 2 | 3.2
| 3.3 | I want to play against a MEDIUM AI, one who uses a limited depth min-max algorithm to determine its next move to make. | 5 | 3.3
| 3.4 | I want to play against a HARD AI, one who uses alpha-beta pruning combined with the min max algortihm, to determine its next move. | 5 | 3.4
| 3.5 | I want to play against an adaptable AI, one who adjusts its dificulty based on my play (optional) | 4 | 3.5
GUI client | 4
| 4.1 | I want to open a connection(socket) with a server | 1 | 4.1
| 4.2 | I want to be able to input the server I want to connect to | 1 | 4.2
| 4.3 | I want to use a graphical interface (text box with a connect button) to open a connection | 3 | 4.3
| 4.4 | I want to know(report) when a connection fails or times out | 1 | 4.4
| 4.5 | I want to be able to click a drop down arrow on my text box that stores a list of recent connections(optional) | 2 | 4.5